## Speedometer
Speedometer |  | Pointer
Start | 0 | Value | 80
Initial | 15 | Pointer | 2
Mid | 45 | End | 118
End | 40 | cpi
Max | 100
Note on D2: joe: The speed where the needle points =INT(E5*100)
Note on A3: joe: Red
Note on D3: joe: The size of the pointer
Note on A4: joe: Yellow
Note on D4: joe: Formula of chart total (200) minute the total of the value and the pointer. =200-(e2+e3)
Note on A5: joe: Green
Note on A6: joe: Sum of Start, Initial, Mid, and End

## Application With EVM
What is the project budget? | 750000
How complete is the project? | 65%
How complete should the project be? | 70%
How much has the project spent? | 510000
Budget at completion | 750000
Actual costs | 510000
Earned value | 487500
Planned value | 525000
Cost variance | -22500
Schedule variance | -37500
Cost performance index | 0.95588
Schedule performance index | 0.92857
Estimate at completion | 784615.3846
Estimate to complete | 274615.3846
To-complete performance index (BAC) | 1.0938
To-complete performance index (EAC) | 0.95588
Variance at completion | -34615.3846

## Practice
Speedometer |  | Pointer
Start | 0 | Value | 85
Initial | 15 | Pointer | 1
Mid | 45 | End | 114
End | 40
Max | 100
Note on D2: joe: The speed where the needle points
Note on A3: joe: Red
Note on D3: joe: The size of the pointer
Note on A4: joe: Yellow
Note on D4: joe: Formula of chart total (200) minute the total of the value and the pointer. =200-(e2+e3)
Note on A5: joe: Green
Note on A6: joe: Sum of Start, Initial, Mid, and End