## Charter
Project Charter
Project Information
Project Name | Network Migration Project
Project Sponsor | Marla Heiz
Project Manager | Ben Wilson
Email Address | ben@instructing.com
Phone Number | 555-867-5309
Organizational Unit | IT
Today's date | 2016-02-01
Project start date | 2016-02-21
Expected Completion Date | 2016-07-01
Summary Budget | 1400000
Project charted authorized by | Marla Heiz
Project approved on | 2016-02-02
Project Goals and Deliverables
Project purpose | To upgrade current network technologies to a faster, more reliable platform.
Business case | Improve operations and usage networking technologies. Increase speed of work and reliability of network for ABC Co.'s employees.
Goals/Metrics | Budget: with 5 percent of 1.4M; With 10 days of target completion date.
Expected outcomes | Current network sunset; new network running and functional by July 1, 2016.
Key Performance Indicators | Throughput increased; security enhancement; faster desktops and laptops; more specific information to come.
Key Milestones in Project | Workstations replaced; servers replaces; new network installed; decommissioned network.
High-Level Risks, Constraints, and Assumptions
Constraints | Assumptions | Initial Risks
Access to workstations | Hardware delivery on time | Server room build project is lagging; may affect this project
Must have all workstations before install | Server room build-out complete | Workstation delivery could affect schedule.
All servers must be on-site prior to conversion | Install testing complete in time | Company holiday on June 8.
Server room build-out must be completed before 2/21 | Data integrity confirmed | Some weekend work will be needed.
Dual-support while converting clients | Network install in plenum won't interrupt business
Data integrity must be confirmed before conversion | Resoruces for project will be available
Must not interrupt business | Help desk is prepared for new OS and configurations
Note on A20: JDP: Is the project worth the investment? Consider documenting: Business case Organizational need Customer request Technology advancements Legal requirements

## Scope document
Project Scope & Requirements
Project Name | Network Migration Project
Project summary | To upgrade current network technologies to a faster, more reliable platform.
Solution summary
Project objectives | Phases | Milestone Schedule | Resources | Budget
Migrate to new Server OS | Phase One: Pre-Migration Planning | 2016-02-01 | Network engineer | 1400000
Migrate all company workstation to new OS | Phase Two: Project Launch |  | Network engineer
Install new networking components | Phase Three: Technology Landscape Analysis |  | Database admin lead
| Phase Four: Build & Test |  | Database admin
| Phase Five: Execution |  | Workstation specialist
| Phase Six: Decommission and Monitor | 2016-07-01 | Workstation specialist
Workstation specialist
Electrician
Electrician
Electrician
Cisco expert
Cisco expert
Business analyst
Business analyst
Network tester
Network tester
Help desk staff
Help desk staff
Documentation/writer
Documentation/writer
Trainer
Trainer
Instructional designer
Instructional designer
Communications expert
Communications expert
Project manager
Project management assistant
Team lead
Scheduler

## WBS
Work Breakdown Structure/Activity List
Project Deliverable | Responsible Resource | Duration | Cost | Notes
Phase One: Pre-Migration Planning | Antonietta | 5 | 400
Impact assessment | Brittny | 3 | 240
Cost analysis | Avril | 1 | 95
Resource requirements | Christoper | 2 | 280
Stakeholder planning | Codi | 2 | 90
Security planning | Prince | 25 | 1250
Project roles and responsibilities | Codi | 45 | 2025
Resource gap analysis | Fawn | 85 | 6800
Phase Two: Project Launch | Brittny | 50 | 4000
Stakeholder register | Ben Wilson | 98 | 9702
Kickoff meeting | Alfonso | 56 | 3640
Procurement processes
Data migration rules
Phase Three: Technology Landscape Analysis
Hardware requirements
Software requirements
Technology inventory
System retirement strategy
New network design topology
New hardware specifications
Data quality management
Phase Four: Build & Test
Migration documentation
Migration test in lab
Migration validation
Migration rollback policy
Migration rollback testing
Phase Five: Execution
Security server migration
Migration validation
Data server migration
Data validation
Print server migration
Migration wave one - workstations
Validation of migration
Migration wave two - workstations
Validation of migration
Migration wave three - workstations
Validation of migration
Migration wave four - workstations
Validation of migration - workstations
Migration wave five
Validation of migration - workstations
Phase Six: Decommission and Monitor
Sunset servers
Data quality monitoring

## Resources
Resource Names | Role | Project Rate | Resource Names | Role | Project Rate
Adan | Server support specialist | 45 | Ben Wilson | Project manager | 150
Alfonso | Electrician | 65 | Louisa | Network architect | 165
Antonietta | Data engineer | 80 | Kristopher | Network architect | 140
Avril | Cisco associate | 95 | Christoper | Network engineer | 140
Ben Wilson | Project manager | 99 | Helen | Network engineer | 140
Brittny | Data engineer | 80 | Soledad | Developer | 85
Christoper | Network engineer | 140 | Tish | Developer | 85
Codi | Server support specialist | 45 | Lakenya | Cisco expert | 160
Fawn | Data engineer | 80 | Avril | Cisco associate | 95
Helen | Network engineer | 140 | Fawn | Data engineer | 80
Kristopher | Network architect | 140 | Brittny | Data engineer | 80
Lakenya | Cisco expert | 160 | Antonietta | Data engineer | 80
Louisa | Network architect | 165 | Alfonso | Electrician | 65
Lynne | Communications | 65 | Norbert | Electrician | 65
Marianela | SME - data servers | 165 | Codi | Server support specialist | 45
Maurine | Help desk support | 50 | Adan | Server support specialist | 45
Norbert | Electrician | 65 | Sunday | SME - networking | 165
Prince | Help desk support | 50 | Marianela | SME - data servers | 165
Soledad | Developer | 85 | Prince | Help desk support | 50
Sunday | SME - networking | 165 | Maurine | Help desk support | 50
Tish | Developer | 85 | Lynne | Communications | 65

## Risk Log
Risk Name | Probability | Impact | Score | Status | Response
Server room build may be late | 0.25 | 80000 | 20000
Workstation delivery may be delayed from vendor | 0.88 | 5000 | 4400
Cisco consultant has a a conflict at start of project | 0.45 | 2500 | 1125
Team member retires | 0.45 | 40000 | 18000
| 0.2 |  | 0